## Backlog
minibench-bot v1 backlog
Implementation-ready issues · Checked 2026-07-20 · Filter by epic, priority, owner or status
ID | Epic | Task | Description | Dependency | Priority | Suggested Owner | Acceptance Criteria | Estimated Complexity | Status | Source or Decision Reference
M0-001 | Repository Foundation | Scaffold Python 3.11 project | Create the public src-layout package, pyproject, README, licence, ignore rules and CLI entry point. | None | Critical | Claude Code | Clean install on Python 3.11; `minibench-bot --help` works; no secrets or generated data tracked. | S | Done | D14; CODEX_HANDOFF First GitHub issue
M0-002 | Repository Foundation | Pin runtime dependencies | Pin forecasting-tools 0.2.92 and test/runtime dependencies; add an explicit upgrade check. | M0-001 | Critical | Claude Code | Lock resolves on Python 3.11; installed package reports 0.2.92; CI fails on drift. | S | Done | https://pypi.org/project/forecasting-tools/
M0-003 | Repository Foundation | Add CI quality gate | Run unit/schema tests, formatting and type checks on supported Python versions. | M0-001 | High | Claude Code | Pull requests run deterministic offline checks and publish a clear pass/fail result. | S | Done | D15
M0-004 | Repository Foundation | Create environment verifier | Validate config, required directories and provider credentials without printing secret values. | M0-002; M0-005 | Critical | Claude Code | `verify-env` reports missing variable names only; exits non-zero on invalid live-submit settings. | S | Done | D11; config.example.yaml
M0-005 | Repository Foundation | Implement typed configuration | Create Pydantic settings matching config.example.yaml with safe defaults and cross-field validation. | M0-001 | Critical | Claude Code | Valid example loads after replacing model placeholder; invalid live-submit combinations are rejected. | M | Done | D11; D27
M0-006 | Documentation | Write local quick start | Document venv, config, environment variables, dry run and test commands. | M0-004 | Medium | Claude Code | A clean checkout can reach the offline dry-run fixture using only documented commands. | S | Done | CODEX_HANDOFF
M0-101 | Metaculus Integration | Wrap MetaculusClient construction | Instantiate one client with configured base URL, token, timeout and pacing. | M0-005 | Critical | Claude Code | Client uses METACULUS_TOKEN and configured pacing; secret is redacted from logs. | S | Done | https://github.com/Metaculus/forecasting-tools/blob/main/forecasting_tools/helpers/metaculus_client.py
M0-102 | Metaculus Integration | Fetch current MiniBench questions | Fetch open questions with configured tournament ID and group-question mode. | M0-101 | Critical | Claude Code | Fixture and live-read modes return typed questions; current alias can be overridden without code changes. | M | Done | https://github.com/Metaculus/forecasting-tools/blob/main/forecasting_tools/helpers/metaculus_client.py ¦ https://www.metaculus.com/tournament/minibench/
M0-103 | Metaculus Integration | Save and reload question snapshots | Persist normalized API snapshots for deterministic replay and tests. | M0-102 | High | Claude Code | Saved snapshot round-trips without network access and retains question/post/tournament IDs. | S | Done | D12
M0-104 | Metaculus Integration | Add bot-testing-area fixture path | Support smoke-test targeting without changing MiniBench config. | M0-102 | High | Claude Code | CLI can target `bot-testing-area` explicitly; production MiniBench remains unchanged. | S | Done | https://github.com/Metaculus/metac-bot-template/blob/main/main.py
M1-201 | Question Normalization | Define canonical question model | Map package question objects into a stable internal schema. | M0-103 | Critical | Claude Code | Golden binary, multiple-choice and numeric fixtures validate and retain resolution fine print. | M | In Review | D20; D21
M1-202 | Question Normalization | Handle group-question unpacking | Preserve group parent identity while processing each subquestion as a forecastable record. | M1-201 | High | Claude Code | Unpacked fixtures produce one unique internal question per subquestion and no duplicate IDs. | M | In Review | https://github.com/Metaculus/forecasting-tools
M1-203 | Question Normalization | Reject unsupported types safely | Flag date/conditional types as deferred instead of coercing or submitting. | M1-201 | High | Claude Code | Unsupported types create a diagnostic event and make zero model/submission calls. | S | Not Started | D21
M1-301 | Retrieval | Define research-document schema | Normalize provider results with stable source IDs, URLs, timestamps, hashes and reliability tags. | M0-005 | Critical | Claude Code | Pydantic schema preserves original URL, published/retrieved times and raw artifact reference. | M | Not Started | D17-D19
M1-302 | Retrieval | Implement AskNews adapter | Retrieve current and historical news while retaining article-level provenance. | M1-301 | Critical | Claude Code | Mocked call returns normalized documents; missing credentials fail before a paid call. | M | Not Started | https://docs.asknews.app/
M1-303 | Retrieval | Implement Exa fallback | Use Exa only when AskNews fails or when official-source/web retrieval is required. | M1-301 | High | Claude Code | Configured fallback records why it ran and preserves citations; no silent provider switching. | M | Not Started | https://exa.ai/pricing
M1-304 | Retrieval | Add structured-source router | Bypass general retrieval for configured official datasets such as FRED and authoritative resolution sources. | M1-301 | Medium | Claude Code | Router produces the same normalized document/observation format and records endpoint parameters. | M | Not Started | https://fred.stlouisfed.org/docs/api/fred/overview.html ¦ D19
M1-305 | Retrieval | Deduplicate and freshness-tag evidence | Canonicalize URLs, hash content and mark documents outside the question-specific freshness window. | M1-301 | High | Claude Code | Duplicate reports collapse without losing provenance; stale evidence is flagged deterministically. | M | Not Started | D17
M1-306 | Retrieval | Persist replayable retrieval runs | Save queries, provider configs, raw responses, costs and normalized documents. | M1-302; M1-303 | Critical | Claude Code | Replay produces zero provider calls and the same research packet hash. | M | Not Started | D12; D16
M1-401 | Forecast Generation | Version and hash the prompt | Load prompts/forecaster.md, verify declared version and compute a content hash. | M0-005 | Critical | Claude Code | Every forecast stores prompt version/hash; changed bytes produce a new hash. | S | Not Started | D4; prompts/forecaster.md
M1-402 | Forecast Generation | Implement structured model call | Call one configured GeneralLlm model with a question-specific Pydantic response type. | M1-401; M1-306 | Critical | Claude Code | Valid response returns typed output; malformed output gets at most one bounded repair attempt. | M | Not Started | https://github.com/Metaculus/forecasting-tools
M1-403 | Forecast Generation | Implement binary output path | Produce probability_yes plus attribution fields. | M1-402 | Critical | Claude Code | Golden output validates within configured bounds and includes base rate, adjustments and failure modes. | S | Not Started | prompts/forecaster.md
M1-404 | Forecast Generation | Implement multiple-choice output path | Produce every exact option once with probabilities summing to one. | M1-402 | High | Claude Code | Unknown/missing/duplicate options fail validation; tolerance is 1e-6. | S | Not Started | prompts/forecaster.md
M1-405 | Forecast Generation | Implement numeric percentile path | Produce the nine declared percentiles for conversion by forecasting-tools. | M1-402 | Critical | Claude Code | Percentile levels are exact; values are finite, ordered and compatible with question bounds. | M | Not Started | https://github.com/Metaculus/forecasting-tools/blob/main/forecasting_tools/data_models/numeric_report.py ¦ prompts/forecaster.md
M1-406 | Forecast Generation | Persist raw output and replay | Store provider response, parsed result, model settings and cost separately from canonical rationale. | M1-402; M1-601 | High | Claude Code | Model replay makes zero API calls and reproduces the parsed forecast hash. | M | Not Started | D12; D24
M1-501 | Validation and Calibration | Validate common attribution fields | Require prior/base rate, status quo, evidence links, load-bearing facts, failure modes and final output. | M1-403 | Critical | Claude Code | Schema rejects missing or unknown required fields and invalid source IDs. | M | Not Started | D4; D24
M1-502 | Validation and Calibration | Validate categorical forecasts | Apply binary bounds and exact multiple-choice normalization. | M1-403; M1-404 | Critical | Claude Code | Boundary and sum tests pass; no arbitrary post-hoc renormalization is hidden. | S | Not Started | https://github.com/Metaculus/forecasting-tools/blob/main/forecasting_tools/helpers/metaculus_client.py
M1-503 | Validation and Calibration | Build and validate numeric CDF | Use NumericDistribution.from_question and get_cdf to produce the submission array. | M1-405 | Critical | Claude Code | Exactly 201 monotone values for normal numeric questions; maintained PMF constraint passes. | M | Not Started | https://github.com/Metaculus/forecasting-tools/blob/main/forecasting_tools/data_models/numeric_report.py
M1-504 | Validation and Calibration | Add stale/insufficient research gate | Flag or fail according to config before approval. | M1-305; M1-501 | High | Claude Code | No-sources and stale-only fixtures produce explicit states and never pass silently. | S | Not Started | config.example.yaml
M1-601 | Attribution Ledger | Create initial SQLite migration | Create append-only forecast, research, document, approval, submission, resolution and score tables. | M0-001 | Critical | Claude Code | Fresh migration succeeds with WAL/foreign keys; unique version/idempotency constraints exist. | M | Done | D16; CODEX_HANDOFF Ledger design
M1-602 | Attribution Ledger | Persist immutable forecast versions | Append one record per forecast version with parent linkage and canonical JSON. | M1-601; M1-501 | Critical | Claude Code | Updating a question appends v2; v1 remains byte-identical. | M | Not Started | D25
M1-603 | Attribution Ledger | Record lifecycle events atomically | Persist validation, approval, submission and failure events in transactions. | M1-601 | Critical | Claude Code | Injected failures cannot leave an approved/submitted state without its event record. | M | Not Started | D25
M1-604 | Attribution Ledger | Export JSONL and Parquet | Create analysis-friendly derived exports for audit and polygraph use. | M1-602 | Medium | Claude Code | Exports round-trip record IDs/counts and never mutate SQLite. | M | Not Started | D29
M1-605 | Attribution Ledger | Add secret and trace redaction | Exclude credentials and hidden chain-of-thought from persisted records/logs. | M1-601 | Critical | Codex | Fixture secrets do not appear in database, exports or logs; rationale remains concise/auditable. | S | Not Started | D24
M2-701 | Submission | Implement approval commands | Approve or reject the exact forecast hash as append-only events. | M1-603 | Critical | Claude Code | Changed forecast invalidates prior approval; actor/timestamp/note are retained. | M | Not Started | D12; D23
M2-702 | Submission | Generate idempotency keys | Derive keys from tournament, question, forecast version and payload hash. | M1-602 | Critical | Claude Code | Same payload/key cannot create two attempts; changed payload requires a new approval/key. | S | Not Started | D23
M2-703 | Submission | Implement dry-run gateway | Return a deterministic receipt without any Metaculus write. | M2-702 | Critical | Claude Code | Dry run records payload/hash and makes zero HTTP post calls. | S | Not Started | CODEX_HANDOFF Submission seam
M2-704 | Submission | Implement package-backed gateway | Call public post methods after approval, capture exceptions and verify by refetch. | M2-701; M2-702 | Critical | Claude Code | Success requires refetch confirmation; uncertain timeout blocks blind retry. | L | Not Started | https://github.com/Metaculus/forecasting-tools/blob/main/forecasting_tools/helpers/metaculus_client.py
M2-705 | Submission | Spike exact response capture | Decide whether refetch receipt is sufficient or add a contract-tested narrow HTTP adapter. | M2-704 | High | Codex | Decision and test evidence recorded; no private package method dependency without a guard. | M | Not Started | R-004; D28
M2-706 | Submission | Run bot-testing-area smoke test | Submit one explicit owner-approved test forecast and persist receipt/refetch. | M2-704 | Critical | Chris + Codex | Forecast appears on bot profile; ledger has approval, payload, attempt and verification snapshot. | M | Blocked | Requires METACULUS_TOKEN
M3-707 | Submission | Submit first MiniBench forecast | Process one current eligible question with human approval. | M2-706 | Critical | Chris + Codex | One live forecast succeeds once; complete pre-resolution record and verified receipt exist. | M | Blocked | Milestone 2 owner approval
M4-801 | Resolution and Scoring | Ingest resolution snapshots | Fetch outcomes/annulments and append resolution events. | M3-707 | High | Claude Code | Resolved fixture updates only via append event; annulled/ambiguous outcomes are not scored. | M | Not Started | https://github.com/Metaculus/forecasting-tools/blob/main/forecasting_tools/helpers/metaculus_client.py
M4-802 | Resolution and Scoring | Compute binary and multiclass scores | Calculate Brier and log scores with versioned implementations. | M4-801 | High | Claude Code | Known examples match hand calculations; extreme probabilities are handled safely. | M | Not Started | https://www.metaculus.com/help/scores-faq/
M4-803 | Resolution and Scoring | Ingest numeric platform scores | Record platform numeric/log/peer scores instead of claiming an unverified local replica. | M4-801 | Medium | Claude Code | Numeric record identifies score source and does not label a proxy as Metaculus score. | M | Not Started | D30
M5-804 | Resolution and Scoring | Generate attribution report dataset | Group outcomes by domain, type, model, prompt and reasoning tags. | M4-802; M4-803; M1-604 | Medium | Claude Code | Export contains counts, calibration bins and score summaries with small-sample warnings. | L | Not Started | Primary objective
T-901 | Testing | Create golden schema fixtures | Add valid/invalid binary, multiple-choice and numeric records. | M1-201; M1-501 | Critical | Claude Code | Fixtures cover all required fields, bounds and malformed outputs. | M | Not Started | CODEX_HANDOFF Test requirements
T-902 | Testing | Mock Metaculus integration | Test fetch, post, timeout, 429/5xx and refetch verification paths. | M0-102; M2-704 | Critical | Claude Code | No live network calls in CI; uncertain-outcome path blocks duplicate submit. | L | Not Started | CODEX_HANDOFF Test requirements
T-903 | Testing | Add dry-run acceptance test | Exercise one saved question through research/model replay to complete ledger record. | M1-306; M1-406; M1-602 | Critical | Codex | One command produces one validated record, zero provider calls and zero submission calls. | M | Not Started | Milestone 1
T-904 | Testing | Add numeric CDF contract tests | Guard 201-point size, monotonicity, bounds and PMF steps against package upgrades. | M1-503 | Critical | Codex | Golden edge cases pass on 0.2.92; dependency drift triggers a visible failure. | M | Not Started | https://github.com/Metaculus/forecasting-tools/blob/main/forecasting_tools/data_models/numeric_report.py
D-1001 | Documentation | Write operator runbook | Document dry run, review, approval, submission, uncertain timeout and recovery. | M2-704 | High | Claude Code | Another operator can recover from each failure state without editing the database. | M | Not Started | D23; R-004
D-1002 | Documentation | Document schemas and exports | Explain ledger lifecycle, immutable versions and polygraph export contract. | M1-604 | Medium | Claude Code | Every table/field and export version has an auditable definition. | M | Not Started | D16; D25; D29
A-1101 | Tournament Administration | Create bot account and token | Create the Metaculus bot identity and store METACULUS_TOKEN securely. | None | Critical | Chris | Bot profile exists; token works in verify-env and is absent from repository/history. | S | Blocked | https://www.metaculus.com/futureeval/participate/
A-1102 | Tournament Administration | Select and authorize model route | Choose an accessible current frontier model and set provider credentials. | M0-005 | Critical | Chris | Verified LiteLLM model name completes one structured fixture call within cost cap. | S | Blocked | D27; owner decision
A-1103 | Tournament Administration | Obtain retrieval credentials | Create AskNews API key and optional Exa fallback key. | None | High | Chris | verify-env recognizes keys; one citation-retaining test query succeeds. | S | Blocked | https://docs.asknews.app/ ¦ https://exa.ai/pricing
A-1104 | Tournament Administration | Confirm current MiniBench eligibility | Read current rules and confirm bot/prize/payout requirements before live batch. | A-1101 | High | Chris | Eligibility, payout identity, update rules and admin deadlines are recorded in Verified Facts. | S | Blocked | https://www.metaculus.com/notebooks/38928/futureeval-resources-page/ ¦ R-001
A-1105 | Tournament Administration | Complete required post-round administration | Complete any survey or payout steps applicable to the entered tournament. | M3-707; A-1104 | Medium | Chris | Required forms are submitted by the official deadline and evidence is recorded privately. | S | Not Started | https://www.metaculus.com/notebooks/43340/summer-futureeval-announcement/

## Verified Facts
Verified facts register
Primary-source claims, checked dates and unresolved implementation dependencies
Topic | Claim | Status | Primary Source | Source Date | Checked Date | Confidence | Implementation Impact | Notes
Program | FutureEval is Metaculus's current AI forecasting benchmark brand. | Verified | https://www.metaculus.com/futureeval/methodology/ | Current page | 2026-07-09 | High | Use FutureEval naming in docs and metadata. | Former AIB naming remains in some code/URLs.
MiniBench cadence | MiniBench is a back-to-back, approximately two-week rapid-feedback series. | Verified | https://www.metaculus.com/aib/minibench/ | Current page | 2026-07-09 | High | Architecture should support fast configuration changes and replay. | Public copy calls it bi-weekly.
Active MiniBench | Current series runs 2026-06-29 through 2026-07-18. | Verified | https://www.metaculus.com/tournament/minibench/ | Current page | 2026-07-09 | High | Immediate target window. | Dates shown on public series page.
Active MiniBench | Current series lists 59 questions and a USD 1,000 prize pool. | Verified | https://www.metaculus.com/tournament/minibench/ | Current page | 2026-07-09 | High | Batch size and external feedback context. | 59 is series count, not verified open/eligible count.
Eligible count | Exact currently open and bot-eligible question count is not established by the public page. | Unresolved | https://www.metaculus.com/tournament/minibench/ | Current page | 2026-07-09 | High | Must fetch under bot token before sizing a run. | Do not equate series count with eligible count.
Seasonal tournament | Summer 2026 FutureEval runs 2026-05-18 through 2026-09-06 with USD 50,000 prize pool. | Verified | https://www.metaculus.com/tournament/summer-futureeval-2026/ | Current page | 2026-07-09 | High | Secondary venue and future expansion path. | Page listed 212 questions when checked.
Participation | Create an account, create a bot, copy its access token, then run a bot/template. | Verified | https://www.metaculus.com/futureeval/participate/ | Current page | 2026-07-09 | High | Owner must create bot/token. | Human account action required.
Model credits | Metaculus states seasonal-tournament inference costs are covered by OpenAI, Anthropic and Google. | Verified | https://www.metaculus.com/futureeval/participate/ | Current page | 2026-07-09 | Medium | May reduce seasonal cost. | Does not establish MiniBench coverage.
Model credits | Free inference for MiniBench was not established by the reviewed official pages. | Unresolved | https://www.metaculus.com/futureeval/participate/ | Current page | 2026-07-09 | High | Owner must authorize/fund v1 model route. | Treat as paid until confirmed.
Administration | The Summer announcement states a survey is required for prizes. | Verified | https://www.metaculus.com/notebooks/43340/summer-futureeval-announcement/ | 2026-05-01 | 2026-07-09 | Medium | Track tournament-specific admin requirements. | Exact deadline not captured in public extract.
MiniBench admin | MiniBench-specific eligibility, payout and post-round steps were not fully verified. | Unresolved | https://www.metaculus.com/notebooks/38928/futureeval-resources-page/ | Edited 2026-07-07 | 2026-07-09 | High | Owner rule check before live batch. | Do not assume seasonal rules are identical.
Scoring | Metaculus scores are underpinned by proper log scores; Peer score compares log score with other forecasts. | Verified | https://www.metaculus.com/help/scores-faq/ | Current page | 2026-07-09 | High | Retain log/peer/platform scores and avoid unjustified extremes. | Local attribution also records Brier where applicable.
Scoring | Forecasts are time-averaged and coverage rewards earlier active predictions. | Verified | https://www.metaculus.com/help/scores-faq/ | Current page | 2026-07-09 | High | After safe pipeline, batch promptly rather than waiting for perfect research. | Human approval remains required initially.
Question types | Binary questions are present in the active MiniBench. | Verified | https://www.metaculus.com/questions/44303/ | Current question | 2026-07-09 | High | Binary path required for Milestone 1. | Public question tagged MiniBench.
Question types | Numeric questions are present in the active MiniBench. | Verified | https://www.metaculus.com/questions/44327/ | Current question | 2026-07-09 | High | Numeric path/CDF required for batch completeness. | Public question tagged MiniBench.
Question types | Presence/count of multiple-choice questions in the active MiniBench was not verified. | Unresolved | https://www.metaculus.com/tournament/minibench/ | Current page | 2026-07-09 | Medium | Implement MC defensively because package/seasonal venue supports it. | Confirm by authenticated fetch.
Question types | Presence/count of group posts in the active MiniBench was not verified. | Unresolved | https://www.metaculus.com/tournament/minibench/ | Current page | 2026-07-09 | Medium | Use unpack_subquestions and retain parent identity. | Confirm by authenticated fetch.
Package | Latest PyPI release checked is forecasting-tools 0.2.92, released 2026-05-27. | Verified | https://pypi.org/project/forecasting-tools/ | 2026-05-27 | 2026-07-09 | High | Pin exact v1 version. | Project is beta/experimental.
Package | Package requires Python >=3.11 and <4.0. | Verified | https://pypi.org/project/forecasting-tools/ | 2026-05-27 | 2026-07-09 | High | Use Python 3.11 baseline. | PyPI classifiers include 3.11-3.14.
Package | Installation is `pip install forecasting-tools`. | Verified | https://pypi.org/project/forecasting-tools/ | 2026-05-27 | 2026-07-09 | High | Use pinned equivalent in pyproject. | Do not float in CI.
Authentication | MetaculusClient reads METACULUS_TOKEN and sends Token authentication. | Verified | https://github.com/Metaculus/forecasting-tools/blob/main/forecasting_tools/helpers/metaculus_client.py | Current source | 2026-07-09 | High | Secret/env validation required. | Never log token.
Tournament ID | CURRENT_MINIBENCH_ID is the string `minibench`. | Verified | https://github.com/Metaculus/forecasting-tools/blob/main/forecasting_tools/helpers/metaculus_client.py | Current source | 2026-07-09 | High | Config default/alias; permit override. | Rotating SDK constants require checks.
Tournament ID | Summer 2026 FutureEval tournament ID is 33022. | Verified | https://github.com/Metaculus/forecasting-tools/blob/main/forecasting_tools/helpers/metaculus_client.py | Current source | 2026-07-09 | High | Secondary target metadata. | CURRENT_AI_COMPETITION_ID points to it.
Fetching | get_all_open_questions_from_tournament accepts int¦string ID and defaults group mode to unpack_subquestions. | Verified | https://github.com/Metaculus/forecasting-tools/blob/main/forecasting_tools/helpers/metaculus_client.py | Current source | 2026-07-09 | High | Use package fetch/normalization path. | Method is synchronous and internally runs async filter.
Supported types | Package question models support binary, multiple-choice, numeric and date; current template also handles conditional types. | Verified | https://github.com/Metaculus/forecasting-tools ¦ https://github.com/Metaculus/metac-bot-template/blob/main/main.py | Current source | 2026-07-09 | High | V1 supports first three; date/conditional deferred. | Summer template says date/conditional are not used in Summer tournament.
Numeric CDF | Normal numeric forecasts use a 201-point CDF. | Verified | https://github.com/Metaculus/forecasting-tools/blob/main/forecasting_tools/data_models/numeric_report.py | Current source | 2026-07-09 | High | Use NumericDistribution conversion/validation. | Do not ask model for 201 raw points.
Numeric CDF | Maintained standardization caps maximum adjacent inbound PMF at 0.2 for the default 200 inbound outcomes. | Verified | https://github.com/Metaculus/forecasting-tools/blob/main/forecasting_tools/data_models/numeric_report.py | Current source | 2026-07-09 | High | Add contract tests around package behavior. | Validator uses 0.95 wiggle room internally.
Binary bounds | Public client posting method requires probability between 0.001 and 0.999. | Verified | https://github.com/Metaculus/forecasting-tools/blob/main/forecasting_tools/helpers/metaculus_client.py | Current source | 2026-07-09 | High | Config and schema bounds must agree. | Inclusive values accepted by guard.
Submission response | Public posting methods return None and raise on failure; they do not expose the HTTP response. | Verified | https://github.com/Metaculus/forecasting-tools/blob/main/forecasting_tools/helpers/metaculus_client.py | Current source | 2026-07-09 | High | Submission seam and verification spike required. | Do not claim complete receipt from SDK alone.
Retries/pacing | Client posting uses retry_with_exponential_backoff; default request spacing is 3.5s with 1s jitter and 30s timeout. | Verified | https://github.com/Metaculus/forecasting-tools/blob/main/forecasting_tools/helpers/metaculus_client.py | Current source | 2026-07-09 | Medium | Reuse defaults/configure explicitly; handle uncertain timeouts. | Exact service rate limits are not published here.
Community prediction | Binary question models can capture community_prediction_at_access_time when API aggregation data is available. | Verified | https://github.com/Metaculus/forecasting-tools/blob/main/forecasting_tools/data_models/questions.py | Current source | 2026-07-09 | Medium | Log snapshot after independent v1 forecast. | Do not use as baseline model input in v1.
Retrieval | AskNews returns article-level URLs, publication dates and summaries and is used by standard FutureEval bots. | Verified | https://docs.asknews.app/ ¦ https://www.metaculus.com/futureeval/methodology/ | Current pages | 2026-07-09 | High | Primary retrieval path. | Retain raw provider response for provenance.
Retrieval cost | AskNews `/news` costs 1 credit for last 48h and 5 credits for archive under current docs. | Verified | https://docs.asknews.app/en/rate-limiting | Current page | 2026-07-09 | Medium | Cost-aware query planning and cache. | Plan/rate limits vary.
Retrieval fallback | Exa advertises a 20,000-request/month free tier; search is USD 7 per 1,000 requests. | Verified | https://exa.ai/pricing | Current page | 2026-07-09 | Medium | Practical fallback with low v1 integration burden. | Owner account availability still required.
Retrieval comparator | Tavily offers 1,000 free credits/month; basic search costs 1 credit and PAYG is USD 0.008/credit. | Verified | https://docs.tavily.com/documentation/api-credits | Current page | 2026-07-09 | Medium | Comparator, not selected v1 fallback. | Would add another SDK/provider path.
Trends | Google Trends API remains an invitation-only alpha. | Verified | https://developers.google.com/search/apis/trends | Current page | 2026-07-09 | High | Do not make Trends a v1 dependency. | Apply only as optional structured source after access.
Canada access | No provider-specific Canadian access restriction was established for AskNews/Exa/Tavily. | Unresolved | https://docs.asknews.app/ ¦ https://exa.ai/pricing ¦ https://docs.tavily.com/documentation/api-credits | Current pages | 2026-07-09 | Low | Owner must confirm account creation/billing from Alberta. | Absence of a published restriction is not proof of access.

## Decisions
Decision register
Locked project constraints plus reversible v1 architecture decisions
Decision ID | Decision | Status | Rationale | Alternatives Considered | Revisit Trigger
D01 | Build an attribution instrument that can also compete. | Locked | Primary value is learning where forecast edge comes from; tournament supplies external feedback. | Tournament-only bot | Never unless project objective changes.
D02 | Use MiniBench/current successor as initial venue. | Locked | Fast feedback and manageable question windows. | Seasonal-only; prediction markets | MiniBench unavailable or technically incompatible.
D03 | Use forecasting-tools wherever it supports the workflow. | Locked | Maintained API/question/CDF glue lowers integration risk. | Raw Metaculus API client | Package blocks attribution or safe submission.
D04 | Freeze attribution schema before first submission. | Locked | Prevents missing pre-resolution data and hindsight contamination. | Add schema after first run | Never for v1.
D05 | Use one strong forecaster model plus retrieval in v1. | Locked | Creates an interpretable baseline. | Model ensemble; Council | After reliable baseline and enough paired questions.
D06 | Do not build the nine-agent Council in v1. | Locked | Complexity would obscure attribution and delay first submission. | Full Council | Milestone 5 complete.
D07 | Reserve multi-agent forecasting for a later A/B test. | Locked | Paired identical questions can measure incremental value. | Immediate multi-agent pipeline | Reliable single-agent baseline exists.
D08 | Do not build continuous Market Pulse updates in v1. | Locked | Different operational problem and cadence. | Always-on updater | Separate post-baseline project.
D09 | Do not integrate PaperPolyMkt. | Locked | Unrelated to first venue and attribution milestone. | Shared trading layer | Explicit new project scope.
D10 | Do not architect around local inference. | Locked | Local machine is for orchestration/storage, not competitive inference. | Local model default | Hardware/model economics materially change.
D11 | Keep model, retrieval, tournament and calibration configurable. | Locked | All are moving external dependencies. | Hard-coded current choices | Never.
D12 | Keep human review before initial submissions. | Locked | Protects live venue and supports learning/debugging. | Autonomous submit | After audited safe batch history and explicit owner decision.
D13 | Prefer a small observable pipeline. | Locked | Fastest route to a trustworthy end-to-end record. | Agent framework/workflow platform | Measured scale requires it.
D14 | Public repository under mcleblanc711. | Locked | Project is intended as a reusable public learning artifact. | Private-only repo | Secrets/licensing issue makes public release unsafe.
D15 | ChatGPT Work researches/specifies; Claude Code may implement; Codex reviews; owner merges. | Locked | Clear division of labour and human merge authority. | Single-tool autonomous merge | Owner changes workflow.
D16 | Use SQLite as v1 source of truth. | Decided | Transactions, uniqueness and local querying beat JSONL for lifecycle/version data without adding infrastructure. | JSONL primary; Parquet primary | SQLite becomes an operational bottleneck.
D17 | Use AskNews as primary retrieval. | Decided | News-specialized, article timestamps/citations, package integration and FutureEval precedent. | Exa; Tavily; provider swarm | Pilot shows poor coverage/cost or credentials unavailable.
D18 | Use Exa as one fallback. | Decided | Package familiarity, broad web/official-source retrieval and simple pricing. | Tavily; Perplexity | Fallback quality or availability fails pilot.
D19 | Bypass general retrieval for authoritative structured sources. | Decided | Direct data reduces transcription errors and improves reproducibility. | Route everything through AskNews/Exa | Source has no stable API/file access.
D20 | Support binary, multiple-choice and numeric in v1. | Decided | Covers verified active types and foreseeable current venue formats. | Binary-only; every package type | Authenticated fetch proves a required unsupported type.
D21 | Defer date and conditional questions. | Decided | Not required by current Summer template and adds validation complexity. | Implement all package types | MiniBench/current successor requires them.
D22 | Log community prediction after forecasting; do not use it as v1 model input. | Decided | Preserves an independent baseline while enabling later comparison. | Give CP to model; omit CP entirely | Explicit experiment tests CP-assisted forecasting.
D23 | Make submission a separate approved command with idempotency. | Decided | Clear safety boundary and duplicate-post protection. | Auto-submit at end of run | Only after explicit safe-autonomy review.
D24 | Store concise rationale summaries, not hidden chain-of-thought. | Decided | Attribution needs auditable factors, not unrestricted internal traces. | Persist full model deliberation | Never without a specific compliant research need.
D25 | Append forecast versions and lifecycle events; never overwrite history. | Decided | Resolution analysis requires exact pre-resolution state. | Mutable current record | Never.
D26 | Pin forecasting-tools 0.2.92 for v1. | Decided | Verified current interface; beta package can change. | Unpinned latest | Reviewed upgrade passes contract tests.
D27 | Require explicit model name; provide no silent model default. | Decided | Provider availability and frontier rankings move faster than code. | Hard-code current leaderboard winner | Owner deliberately pins a stable default.
D28 | Use package post methods plus refetch verification first; spike exact response capture. | Decided | Uses maintained path while addressing receipt gap with a narrow seam. | Private method; raw API from day one | Refetch cannot establish submission outcome.
D29 | Treat JSONL/Parquet as derived exports. | Decided | Supports audit and polygraph analysis without multiple sources of truth. | Parallel primary stores | External consumer requires another canonical format.
D30 | Ingest platform numeric scores before implementing a local replica. | Decided | Avoids mislabelling a proxy metric as Metaculus continuous log score. | Custom numeric scoring immediately | Official formula/API is fully verified and tested.
D31 | Keep current tournament IDs in config and verify SDK aliases at runtime. | Decided | MiniBench slug rotates semantically even when string stays stable; seasonal numeric ID changes. | Hard-code constants in modules | Never.

## Risks
Risk register
Operational, technical and tournament-administration risks for v1
Risk ID | Risk | Probability | Impact | Mitigation | Detection Signal | Owner | Status
R-001 | MiniBench-specific eligibility or payout rule is missed. | Medium | High | Owner verifies current rules before live batch and records deadlines. | Conflicting rule text; missing eligibility badge/payout step. | Chris | Open
R-002 | Active question count/type mix differs from public page assumptions. | High | Medium | Authenticated fetch drives runtime scope; unsupported types fail closed. | Fetched type not in supported set; eligible count differs from 59. | Claude Code | Open
R-003 | forecasting-tools beta update breaks interfaces or CDF behavior. | Medium | High | Pin 0.2.92 and run package contract tests before upgrades. | Dependency drift; CDF golden test failure. | Codex | Mitigated
R-004 | Submission times out after server accepted it, causing duplicate retry risk. | Medium | Critical | Idempotency key, block blind retry, refetch forecast history before retry. | Timeout/no receipt; refetch shows new forecast or remains ambiguous. | Claude Code | Open
R-005 | Public SDK cannot provide complete response receipt. | High | High | Submission seam; record payload/exception/refetch; spike narrow response-capturing adapter. | SDK returns None on successful post. | Codex | Open
R-006 | AskNews credentials/cost make primary retrieval unavailable. | Medium | Medium | Exa fallback; cost caps; raw replay cache. | verify-env failure; 401/402/429; cost limit reached. | Chris | Open
R-007 | Retrieval provides duplicated or stale evidence. | High | High | Canonical URL/content hashes, publication timestamps and freshness flags. | Repeated content hashes; documents outside cutoff. | Claude Code | Open
R-008 | Model output passes JSON parsing but violates forecast semantics. | Medium | High | Strict Pydantic plus question-aware validators and one repair attempt. | Option mismatch; probability sum; unordered percentiles. | Claude Code | Open
R-009 | Community prediction anchors the independent baseline. | Medium | Medium | Exclude CP from prompt; snapshot only after forecast generation. | Research packet contains CP; model rationale cites community. | Codex | Mitigated
R-010 | Attribution record contains hidden chain-of-thought or sensitive data. | Medium | High | Persist concise structured rationale; redact secrets; public-data review. | Long unrestricted reasoning; token/key pattern scan hit. | Codex | Open
R-011 | SQLite/exports diverge. | Low | Medium | SQLite only source of truth; deterministic exports with counts/hashes. | Record count or hash mismatch. | Claude Code | Mitigated
R-012 | Numeric local score is incorrectly presented as Metaculus score. | Medium | High | Ingest platform score first; label any proxy explicitly. | Metric lacks source/implementation version. | Codex | Mitigated
R-013 | Provider model name is invalid or silently routes to a different model. | Medium | High | Require explicit LiteLLM name; record returned model identifier; smoke test. | Provider response model differs; 404/unsupported parameter. | Chris | Open
R-014 | Human approval applies to a stale forecast after content changes. | Medium | Critical | Approval binds exact forecast/payload hash and expires on version change. | Current hash differs from approval event. | Claude Code | Mitigated
R-015 | Public repository leaks tokens or raw private data. | Low | Critical | Env-only secrets, ignore generated data, secret scanning and review gate. | Secret scanner alert; key-like string in git diff. | Chris + Codex | Open
R-016 | Limited Google Trends alpha access becomes a hidden dependency. | Low | Medium | Keep Trends optional and disabled by default. | Run fails without Trends credentials. | Claude Code | Mitigated
R-017 | Model/retrieval spend scales unexpectedly across 59 questions. | Medium | High | Start limit=1, per-run USD cap, sequential processing and replay cache. | Cost manager approaches cap; concurrent calls exceed plan. | Chris | Open